## Initial Plan
Color Coding |  |  |  | Completed |  |  |  |  | SPRING 2023 SEMESTER
In Progress
[7 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[7 empty] | Date | 2023-01-23 | 2023-01-31 | 2023-02-07 | 2023-02-14 | 2023-02-21 | 2023-02-28 | 2023-03-07 | 2023-03-14 | 2023-03-21 | 2023-03-28 | 2023-04-04 | 2023-04-11 | 2023-04-18 | 2023-04-25 | 2023-05-02 | 2023-05-09
Project Phase | Activity |  |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  |  | Yash Kantharia | 2023-01-23 | 2023-01-24 | 100%
| Confirm Project Team Roles |  |  | Yash Kantharia | 2023-01-25 | 2023-01-31 | 100%
| Develop two business cases |  |  | Yash Kantharia/Poonam Adtani/Maneesha Narahari | 2023-01-25 | 2023-01-31 | 100%
| Develop Project Initiation Document (PID) |  |  | ALL | 2023-01-25 | 2023-01-31 | 100%
| Produce initial Project Plan, RACI |  |  | Maneesha / Tharun Reddy | 2023-01-25 | 2023-01-31 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  |  | Yash Kantharia | 2023-02-01 | 2023-02-07 | 100%
| Produce Context Diagram, Define System Interfaces |  |  | Yash Kantharia | 2023-02-01 | 2023-02-07 | 100%
| Define Business Requirements |  |  | Yash Kantharia/Sarvesh Desai/Poonam Adtani | 2023-02-01 | 2023-02-07 | 100%
| Decide which features to implement this semester |  |  | Poonam Adtani | 2023-02-14 | 2023-02-21 | 100%
| Define Functional Decomposition |  |  | Alan Parmar/Sarvesh Desai | 2023-02-22 | 2023-02-28 | 100%
| Produce RCT document |  |  | Alan Parmar/Sarvesh Desai | 2023-02-22 | 2023-02-27 | 100%
| Define functional requirements (User Stories) |  |  | Maneesha/ Tharun Reddy | 2023-02-28 | 2023-03-07 | 100%
| Produce analysis diagrams (UML, DFD) |  |  | Poonam Adtani/Yash Kantharia/Sarvesh Desai | 2023-02-28 | 2023-03-07 | 100%
| Update Project Plan with additional requirements tasks |  |  | Yash Kantharia / Poonam Adtani | 2023-02-07 | 2023-03-07 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (Class, Sequence Diagrams) |  |  | Poonam Adtani/Maneesha Narahari | 2023-03-21 | 2023-03-28 | 100%
| Database Design (ERD, Table spec) |  |  | Maneesha Narahari | 2023-03-21 | 2023-03-28 | 100%
| System Interface Design |  |  | Sarvesh Desai/Poonam Adtani | 2023-03-28 | 2023-04-05 | 100%
| User interface design |  |  | Sarvesh Desai | 2023-04-05 | 2023-04-11 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | Create Account | GUI & Functionality Detailed Design |  | Tharun Reddy | 2023-03-01 | 2023-04-19 | 100%
|  | Coding | Creation of registration page with registration data | Poonam Adtani | 2023-03-01 | 2023-04-19 | 100%
|  |  | Email and Password Validation | Yash Kantharia | 2023-03-01 | 2023-04-19 | 100%
|  |  | Email and Password Encryption | Yash Kantharia | 2023-03-01 | 2023-04-19 | 100%
|  |  | Exception handling cases: Incorrect email or password format, user already exists | Maneesha Narahari | 2023-03-01 | 2023-04-19 | 100%
|  |  | Database connectivity for storing the registration information | Poonam Adtani | 2023-03-01 | 2023-04-19 | 100%
| Modify Account | GUI & Functionality Detailed Design |  | Tharun Reddy | 2023-03-20 | 2023-04-19 | 100%
|  | Coding | Email and Password Validation | Yash Kantharia | 2023-03-20 | 2023-04-25 | 50%
|  |  | Email and Password Encryption | Yash Kantharia | 2023-03-20 | 2023-04-25 | 50%
|  |  | Exception handling cases: Incorrect email or password format, user already exists | Maneesha Narahari | 2023-03-20 | 2023-04-25 | 50%
|  |  | Email and password verification for modifiying data in database | Tharun Reddy | 2023-03-20 | 2023-04-25 | 30%
|  |  | Database connectivity for storing the modified information | Poonam Adtani | 2023-03-20 | 2023-04-25 | 20%
| Login Account | GUI & Functionality Detailed Design |  | Tharun Reddy | 2023-04-02 | 2023-04-25 | 10%
|  | Coding | Exception handling cases: user does not exist, redirect to sign up | Maneesha Narahari | 2023-04-02 | 2023-04-25 | 10%
|  |  | Email and password verification with database to access the website | Poonam Adtani | 2023-04-02 | 2023-04-25 | 10%
| Delete Account | GUI & Functionality Detailed Design |  | Tharun Reddy | 2023-04-02 | 2023-04-25 | 10%
|  | Coding | Database connectivity to delete the existing account details upon successful deletion | Tharun Reddy | 2023-04-02 | 2023-04-25 | 20%
|  |  | Email and password verification with database to delete the account | Poonam Adtani | 2023-04-02 | 2023-04-25 | 10%
| Mail Query | GUI & Functionality Detailed Design |  | Tharun Reddy | 2023-04-02 | 2023-04-25 | 50%
|  | Coding |  | Poonam Adtani | 2023-04-02 | 2023-04-25 | 10%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  |  | Saichand/ Poonam | 2023-04-19 | 2023-04-28 | 0%
| Evaluate Features to be Tested |  |  | ALL | 2023-04-19 | 2023-04-28 | 0%
| Create Account |  | Design Test Cases | Saichand/ Poonam | 2023-04-19 | 2023-04-28 | 0%
|  |  | Execute Test Cases | Saichand/ Poonam | 2023-04-19 | 2023-04-28 | 0%
|  |  | Anaylze Test Results | ALL | 2023-04-19 | 2023-04-28 | 0%
| Modify Account |  | Design Test Cases | Saichand/ Poonam | 2023-04-20 | 2023-04-28 | 0%
|  |  | Execute Test Cases | Saichand/ Poonam | 2023-04-20 | 2023-04-28 | 0%
|  |  | Anaylze Test Results | ALL | 2023-04-20 | 2023-04-28 | 0%
| Login Account |  | Design Test Cases | Saichand/ Poonam | 2023-04-20 | 2023-04-28 | 0%
|  |  | Execute Test Cases | Saichand/ Poonam | 2023-04-20 | 2023-04-28 | 0%
|  |  | Anaylze Test Results | ALL | 2023-04-20 | 2023-04-28 | 0%
| Delete Account |  | Design Test Cases | Saichand/ Poonam | 2023-04-22 | 2023-04-28 | 0%
|  |  | Execute Test Cases | Saichand/ Poonam | 2023-04-22 | 2023-04-28 | 0%
|  |  | Anaylze Test Results | ALL | 2023-04-22 | 2023-04-28 | 0%
| Mail Query |  | Design Test Cases | Saichand/ Poonam | 2023-04-22 | 2023-04-28 | 0%
|  |  | Execute Test Cases | Saichand/ Poonam | 2023-04-22 | 2023-04-28 | 0%
|  |  | Anaylze Test Results | ALL | 2023-04-22 | 2023-04-28 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation PowerPoint |  |  | ALL | 2023-05-02 | 2023-05-09 | 0%