## Initial Plan
Color Coding |  |  | Completed |  |  |  |  | SPRING 2023 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[6 empty] | Date | 2023-01-23 | 2023-01-31 | 2023-02-07 | 2023-02-14 | 2023-02-21 | 2023-02-28 | 2023-03-07 | 2023-03-14 | 2023-03-21 | 2023-03-28 | 2023-04-04 | 2023-04-11 | 2023-04-18 | 2023-04-25 | 2023-05-02 | 2023-05-09
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | Yash Kantharia | 2023-01-23 | 2023-01-24 | 100%
| Confirm Project Team Roles |  | Yash Kantharia | 2023-01-25 | 2023-01-31 | 100%
| Develop two business cases |  | Yash Kantharia/Poonam Adtani/Maneesha Narahari | 2023-01-25 | 2023-01-31 | 100%
| Develop Project Initiation Document (PID) |  | ALL | 2023-01-25 | 2023-01-31 | 100%
| Produce initial Project Plan, RACI |  | Maneesha / Tharun Reddy | 2023-01-25 | 2023-01-31 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Yash Kantharia | 2023-02-01 | 2023-02-07 | 100%
| Produce Context Diagram, Define System Interfaces |  | Yash Kantharia | 2023-02-01 | 2023-02-07 | 100%
| Define Business Requirements |  | Yash Kantharia/Sarvesh Desai/Poonam Adtani | 2023-02-01 | 2023-02-07 | 100%
| Decide which features to implement this semester |  | Poonam Adtani | 2023-02-14 | 2023-02-21 | 100%
| Define Functional Decomposition |  | Alan Parmar/Sarvesh Desai | 2023-02-22 | 2023-02-28 | 100%
| Produce RCT document |  | Alan Parmar/Sarvesh Desai | 2023-02-22 | 2023-02-27 | 100%
| Define functional requirements (User Stories) |  | Maneesha/ Tharun Reddy | 2023-02-28 | 2023-03-07 | 100%
| Produce analysis diagrams (UML, DFD) |  | Poonam Adtani/Yash Kantharia/Sarvesh Desai | 2023-02-28 | 2023-03-07 | 100%
| Update Project Plan with additional requirements tasks |  | Yash Kantharia / Poonam Adtani | 2023-02-07 | 2023-03-07 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (Class, Sequence Diagrams) |  | Poonam Adtani/Maneesha Narahari | 2023-03-21 | 2023-03-28 | 0%
| Database Design (ERD, Table spec) |  | Maneesha Narahari | 2023-03-21 | 2023-03-28 | 0%
| System Interface Design |  | Sarvesh Desai/Poonam Adtani | 2023-04-05 | 2023-04-05 | 0%
| User interface design |  | Sarvesh Desai | 2023-04-05 | 2023-04-11 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | Create Account | GUI & Functionality Detailed Design | Tharun Reddy | 2023-04-12 | 2023-04-12 | 0%
|  | Coding | Poonam Adtani | 2023-04-12 | 2023-04-12 | 0%
| Modify Account | GUI & Functionality Detailed Design | Tharun Reddy | 2023-04-13 | 2023-04-13 | 0%
|  | Coding | Poonam Adtani | 2023-04-13 | 2023-04-13 | 0%
| Login Account | GUI & Functionality Detailed Design | Tharun Reddy | 2023-04-14 | 2023-04-14 | 0%
|  | Coding | Poonam Adtani | 2023-04-14 | 2023-04-14 | 0%
| Delete Account | GUI & Functionality Detailed Design | Tharun Reddy | 2023-04-15 | 2023-04-15 | 0%
|  | Coding | Poonam Adtani | 2023-04-16 | 2023-04-16 | 0%
| Mail Query | GUI & Functionality Detailed Design | Tharun Reddy | 2023-04-17 | 2023-04-17 | 0%
|  | Coding | Poonam Adtani | 2023-04-18 | 2023-04-18 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  | Saichand/ Poonam | 2023-04-19 | 2023-04-19 | 0%
| Evaluate Features to be Tested |  | ALL | 2023-04-19 | 2023-04-19 | 0%
| Create Account | Design Test Cases | Saichand/ Poonam | 2023-04-19 | 2023-04-19 | 0%
|  | Execute Test Cases | Saichand/ Poonam | 2023-04-19 | 2023-04-19 | 0%
|  | Anaylze Test Results | ALL | 2023-04-19 | 2023-04-19 | 0%
| Modify Account | Design Test Cases | Saichand/ Poonam | 2023-04-20 | 2023-04-20 | 0%
|  | Execute Test Cases | Saichand/ Poonam | 2023-04-20 | 2023-04-20 | 0%
|  | Anaylze Test Results | ALL | 2023-04-20 | 2023-04-20 | 0%
| Login Account | Design Test Cases | Saichand/ Poonam | 2023-04-20 | 2023-04-20 | 0%
|  | Execute Test Cases | Saichand/ Poonam | 2023-04-20 | 2023-04-20 | 0%
|  | Anaylze Test Results | ALL | 2023-04-20 | 2023-04-20 | 0%
| Delete Account | Design Test Cases | Saichand/ Poonam | 2023-04-21 | 2023-04-22 | 0%
|  | Execute Test Cases | Saichand/ Poonam | 2023-04-21 | 2023-04-22 | 0%
|  | Anaylze Test Results | ALL | 2023-04-21 | 2023-04-22 | 0%
| Mail Query | Design Test Cases | Saichand/ Poonam | 2023-04-23 | 2023-04-23 | 0%
|  | Execute Test Cases | Saichand/ Poonam | 2023-04-24 | 2023-04-24 | 0%
|  | Anaylze Test Results | ALL | 2023-04-25 | 2023-04-25 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation PowerPoint |  | ALL | 2023-05-02 | 2023-05-09 | 0%