## Road Map
Circular Pie Web Application
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 10/14/23 | Iteration 2 - 11/04/23 | Iteration 3 - 11/18/23 | Iteration 4 - 12/16/23
Module 1 - Account Management | 01.01 Create Account
01.02 Modify Account
01.03 Login Account
01.04 Delete Account
Module 2 - Menu Selection | 02.01 Customize Pizza | 4 | x
| 02.02 Add To Cart | 3 |  | x
| 02.03 View Cart | 2 |  | x
Module 3 - Order Placing | 03.01 Submit Order | 3 |  |  | x |  | Features implemented last sem
| 03.02 Process Order | 4 |  |  | x
| 03.03 Add Special Instructions | 3 |  |  | x
Module 4 - Processing Payments | 04.01 Make Payment | 4 |  |  |  | x
| 04.02 Add Card | 3 |  |  |  | x
| 04.03 Download Invoice | 2 |  |  |  | x
Module 5 - Delivery/Pickup | 05.01 Pickup Order | 3 |  |  |  | x
| 05.02 Update Order Status | 4 |  |  | x
Module 6 - Advertising | 06.01 Create Ads | 3 | x
| 06.02 Modify Ads | 3 |  | x
| 06.03 Delete Ads | 3 |  | x
Module 7 - Customer Support | 07.01 Mail Query
| 07.02 Open Support Ticket | 4 |  | x
| 07.03 Close Support Ticket | 3 |  | x
|  | VELOCITY: | 7 | 18 | 14 | 12

## Story Map
Epics
Epic 1 - Account Management |  | Epic 2 - Menu Selection | Epic 3 - Order Placing | Epic 4 - Processing Payments | Epic 5 - Delivery/Pickup | Epic 6 - Advertising | Epic 7 - Customer Support
Epic 2 - Menu Selection | User Stories | 02.01 Customize Pizza |  |  |  | 06.01 Create Ads |  | Iteration 1
Epic 3 - Order Placing |  | 02.02 Add To Cart |  |  |  | 06.02 Modify Ads | 07.02 Open Support Ticket
Epic 4 - Processing Payments |  | 02.03 View Cart |  |  |  | 06.03 Delete Ads | 07.03 Close Support Ticket | Iteration 2
Epic 5 - Delivery/Pickup |  |  | 03.01 Submit Order |  | 05.02 Update Order Status |  |  | Iteration 3
Epic 6 - Advertising |  |  | 03.02 Process Order
Epic 7 - Customer Support |  |  | 03.03 Add Special Instructions
|  |  |  | 04.01 Make Payment | 05.01 Pickup Order |  |  | Iteration 4
04.02 Add Card
04.03 Download Invoice