## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02. Menu Selection | 2.01 | Customize Pizza | Implement core functionality | 2023-09-29 | 2023-09-30 | 100% | Poonam Adtani
2 | 02. Menu Selection | 2.01 | Customize Pizza | Implement GUI requirments | 2023-09-30 | 2023-10-01 | 100% | Yash Kantharia
3 | 02. Menu Selection | 2.01 | Customize Pizza | Test the different options of pizza dough. | 2023-10-01 | 2023-10-02 | 100% | Poonam Adtani
4 | 02. Menu Selection | 2.01 | Customize Pizza | Test the different options of pizza sauces. | 2023-10-02 | 2023-10-03 | 70% | Yash Kantharia
5 | 02. Menu Selection | 2.01 | Customize Pizza | Test the different options of pizza size. | 2023-10-03 | 2023-10-04 | 100% | Maneesha Narahari
6 | 02. Menu Selection | 2.01 | Customize Pizza | Test the different options of pizza toppings. | 2023-10-04 | 2023-10-05 | 70% | Sarvesh
7 | 02. Menu Selection | 2.01 | Customize Pizza | Ensure customization process doesn't exceed 5 minutes. | 2023-10-05 | 2023-10-05 | 100% | Tharun Reddy
8 | 02. Menu Selection | 2.01 | Customize Pizza | Calculate pizza price depending on the selected items | 2023-10-05 | 2023-10-05 | 80% | Sai chand Reddy
9 | 02. Menu Selection | 2.01 | Customize Pizza | Update Price on Selection Changes | 2023-10-06 | 2023-10-06 | 100% | Alan
10 | 02. Menu Selection | 2.01 | Customize Pizza | Load default price for every selected pizza dough type | 2023-10-07 | 2023-10-07 | 80% | Yash Kantharia
11 | 02. Menu Selection | 2.01 | Customize Pizza | Load default price for every selected pizza sauce | 2023-10-08 | 2023-10-08 | 100% | Sai chand Reddy
12 | 02. Menu Selection | 2.01 | Customize Pizza | Load default price for every selected pizza toppings | 2023-10-09 | 2023-10-09 | 100% | Sarvesh
13 | 06. Advertising | 6.01 | Create Ads | Implement core functionality | 2023-10-09 | 2023-10-09 | 100% | Tharun Reddy
14 | 06. Advertising | 6.01 | Create Ads | Implement GUI requirments | 2023-10-09 | 2023-10-09 | 100% | Alan
15 | 06. Advertising | 6.01 | Create Ads | Define user permissons | 2023-10-10 | 2023-10-10 | 100% | Sarvesh
16 | 06. Advertising | 6.01 | Create Ads | Implement client-side validation for ad format | 2023-10-11 | 2023-10-11 | 80% | Maneesha Narahari
17 | 06. Advertising | 6.01 | Create Ads | Display appropriate error messages if the format is not met | 2023-10-12 | 2023-10-12 | 70% | Yash Kantharia
18 | 06. Advertising | 6.01 | Create Ads | Display the calculated cost to the ad manager | 2023-10-13 | 2023-10-13 | 100% | Alan
19 | 06. Advertising | 6.01 | Create Ads | Develop a mechanism to store the ad data | 2023-10-13 | 2023-10-13 | 100% | Sarvesh
20 | 06. Advertising | 6.01 | Create Ads | Test the ad creation process with different input scenarios | 2023-10-13 | 2023-10-14 | 80% | Maneesha Narahari