## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02. Menu Selection | 2.01 | Customize Pizza | Implement core functionality | 2023-09-29 | 2023-09-30 | 100% | Poonam Adtani
2 | 02. Menu Selection | 2.01 | Customize Pizza | Implement GUI requirments | 2023-09-30 | 2023-10-01 | 100% | Yash Kantharia
3 | 02. Menu Selection | 2.01 | Customize Pizza | Test the different options of pizza dough. | 2023-10-01 | 2023-10-02 | 100% | Poonam Adtani
4 | 02. Menu Selection | 2.01 | Customize Pizza | Test the different options of pizza sauces. | 2023-10-02 | 2023-10-03 | 100% | Yash Kantharia
5 | 02. Menu Selection | 2.01 | Customize Pizza | Test the different options of pizza size. | 2023-10-03 | 2023-10-04 | 100% | Maneesha Narahari
6 | 02. Menu Selection | 2.01 | Customize Pizza | Test the different options of pizza toppings. | 2023-10-04 | 2023-10-05 | 100% | Sarvesh
7 | 02. Menu Selection | 2.01 | Customize Pizza | Ensure customization process doesn't exceed 5 minutes. | 2023-10-05 | 2023-10-05 | 100% | Tharun Reddy
8 | 02. Menu Selection | 2.01 | Customize Pizza | Calculate pizza price depending on the selected items | 2023-10-05 | 2023-10-05 | 100% | Sai chand Reddy
9 | 02. Menu Selection | 2.01 | Customize Pizza | Update Price on Selection Changes | 2023-10-06 | 2023-10-06 | 100% | Alan
10 | 02. Menu Selection | 2.01 | Customize Pizza | Load default price for every selected pizza dough type | 2023-10-07 | 2023-10-07 | 100% | Yash Kantharia
11 | 02. Menu Selection | 2.01 | Customize Pizza | Load default price for every selected pizza sauce | 2023-10-08 | 2023-10-08 | 100% | Sai chand Reddy
12 | 02. Menu Selection | 2.01 | Customize Pizza | Load default price for every selected pizza toppings | 2023-10-09 | 2023-10-09 | 100% | Sarvesh
13 | 06. Advertising | 6.01 | Create Ads | Implement core functionality | 2023-10-09 | 2023-10-09 | 100% | Tharun Reddy
14 | 06. Advertising | 6.01 | Create Ads | Implement GUI requirments | 2023-10-09 | 2023-10-09 | 100% | Alan
15 | 06. Advertising | 6.01 | Create Ads | Define user permissons | 2023-10-10 | 2023-10-10 | 100% | Sarvesh
16 | 06. Advertising | 6.01 | Create Ads | Implement client-side validation for ad format | 2023-10-11 | 2023-10-11 | 100% | Maneesha Narahari
17 | 06. Advertising | 6.01 | Create Ads | Display appropriate error messages if the format is not met | 2023-10-12 | 2023-10-12 | 100% | Yash Kantharia
18 | 06. Advertising | 6.01 | Create Ads | Display the calculated cost to the ad manager | 2023-10-13 | 2023-10-13 | 100% | Alan
19 | 06. Advertising | 6.01 | Create Ads | Develop a mechanism to store the ad data | 2023-10-13 | 2023-10-13 | 100% | Sarvesh
20 | 06. Advertising | 6.01 | Create Ads | Test the ad creation process with different input scenarios | 2023-10-13 | 2023-10-14 | 100% | Maneesha Narahari
21 | 02. Menu Selection | 2.02 | Add To Cart | Implement core functionality | 2023-10-20 | 2023-10-20 | 100% | Poonam Adtani
22 | 02. Menu Selection | 2.02 | Add To Cart | Implement GUI requirments | 2023-10-20 | 2023-10-20 | 100% | Yash Kantharia
23 | 02. Menu Selection | 2.02 | Add To Cart | Test if the customized product is added to the cart | 2023-10-20 | 2023-10-20 | 100% | Poonam Adtani
24 | 02. Menu Selection | 2.02 | Add To Cart | Test if the price of the cart is updated | 2023-10-21 | 2023-10-21 | 70% | Yash Kantharia
25 | 02. Menu Selection | 2.02 | Add To Cart | Stacking the same type of pizza in the cart | 2023-10-21 | 2023-10-21 | 100% | Maneesha Narahari
26 | 02. Menu Selection | 2.02 | Add To Cart | Ensure the customer can add a maximum of 10 pizzas per order | 2023-10-21 | 2023-10-21 | 70% | Sarvesh
27 | 02. Menu Selection | 2.02 | Add To Cart | Emptying the cart if the account is inactive for 30mins | 2023-10-22 | 2023-10-22 | 100% | Tharun Reddy
28 | 02. Menu Selection | 2.02 | Add To Cart | Notifying the customer after emptying the cart | 2023-10-22 | 2023-10-22 | 80% | Sai chand Reddy
29 | 02. Menu Selection | 2.03 | View Cart | Implement core functionality | 2023-10-22 | 2023-10-22 | 100% | Alan
30 | 02. Menu Selection | 2.03 | View Cart | Implement GUI requirments | 2023-10-23 | 2023-10-23 | 80% | Yash Kantharia
31 | 02. Menu Selection | 2.03 | View Cart | Test the dedicated View cart page in the user interface | 2023-10-24 | 2023-10-24 | 100% | Sai chand Reddy
32 | 02. Menu Selection | 2.03 | View Cart | Ensure clear, organized cart view with toppings and customizations | 2023-10-24 | 2023-10-24 | 100% | Sarvesh
33 | 02. Menu Selection | 2.03 | View Cart | Test If empty cart at checkout, show the message to add items | 2023-10-24 | 2023-10-24 | 100% | Tharun Reddy
34 | 02. Menu Selection | 2.03 | View Cart | Display cart cost breakdown: items, taxes, and fees clearly. | 2023-10-25 | 2023-10-25 | 100% | Alan
35 | 06. Advertising | 6.02 | Modify Ads | Implement core functionality | 2023-10-25 | 2023-10-25 | 100% | Sarvesh
36 | 06. Advertising | 6.02 | Modify Ads | Implement GUI requirments | 2023-10-25 | 2023-10-25 | 80% | Maneesha Narahari
37 | 06. Advertising | 6.02 | Modify Ads | Ensure that the authorized user has access to modify the ad | 2023-10-25 | 2023-10-25 | 70% | Yash Kantharia
38 | 06. Advertising | 6.02 | Modify Ads | Tracking the modifications for auditing | 2023-10-26 | 2023-10-26 | 100% | Alan
39 | 06. Advertising | 6.02 | Modify Ads | Display the updated calculated cost to the ad manager | 2023-10-26 | 2023-10-26 | 100% | Sarvesh
40 | 06. Advertising | 6.02 | Modify Ads | Ensure that predefined format is maintained during modifications | 2023-10-26 | 2023-10-26 | 80% | Maneesha Narahari
41 | 06. Advertising | 6.03 | Delete Ads | Implement core functionality | 2023-10-27 | 2023-10-27 | 100% | Poonam Adtani
42 | 06. Advertising | 6.03 | Delete Ads | Implement GUI requirments | 2023-10-27 | 2023-10-27 | 80% | Yash Kantharia
43 | 06. Advertising | 6.03 | Delete Ads | Ensure that only the authorized managers can delete the ad | 2023-10-27 | 2023-10-27 | 70% | Poonam Adtani
44 | 06. Advertising | 6.03 | Delete Ads | Display a confirmation prompt while deleting an ad | 2023-10-28 | 2023-10-28 | 100% | Yash Kantharia
45 | 06. Advertising | 6.03 | Delete Ads | Display an unauthorized access message to unauthorized users | 2023-10-28 | 2023-10-28 | 100% | Maneesha Narahari
46 | 06. Advertising | 6.03 | Delete Ads | Test the ad deletion process | 2023-10-28 | 2023-10-28 | 80% | Sarvesh
47 | 07. Customer Support | 7.02 | Open Support Ticket | Implement basic support ticket creation functionality | 2023-10-29 | 2023-10-29 | 100% | Tharun Reddy
48 | 07. Customer Support | 7.02 | Open Support Ticket | Implement email notifications for ticket creations and status updates | 2023-10-29 | 2023-10-29 | 80% | Sai chand Reddy
49 | 07. Customer Support | 7.02 | Open Support Ticket | Notify the user requesting missing details | 2023-10-30 | 2023-10-30 | 70% | Alan
50 | 07. Customer Support | 7.02 | Open Support Ticket | Implement ticket escalation timer to notify supervisors | 2023-10-30 | 2023-10-30 | 100% | Yash Kantharia
51 | 07. Customer Support | 7.02 | Open Support Ticket | Notify user once the ticket is resolved and request for confirmation | 2023-10-30 | 2023-10-30 | 100% | Sai chand Reddy
52 | 07. Customer Support | 7.02 | Close Support Ticket | Implement close ticket functionality | 2023-10-31 | 2023-10-31 | 80% | Sarvesh
53 | 07. Customer Support | 7.02 | Close Support Ticket | Implement comments/notes section after close action is performed. | 2023-11-01 | 2023-11-01 | 100% | Tharun Reddy
54 | 07. Customer Support | 7.03 | Close Support Ticket | Implement archive functionality for closed tickets | 2023-11-01 | 2023-11-01 | 80% | Alan
55 | 07. Customer Support | 7.03 | Close Support Ticket | Display close option only for support agent roles. | 2023-11-01 | 2023-11-01 | 70% | Sarvesh
56 | 07. Customer Support | 7.03 | Close Support Ticket | Display close option only for resolved tickets. | 2023-11-02 | 2023-11-02 | 100% | Maneesha Narahari
57 | 07. Customer Support | 7.03 | Close Support Ticket | Verify archived tickets accessability for future reference. | 2023-11-02 | 2023-11-02 | 100% | Yash Kantharia
58 | 07. Customer Support | 7.03 | Close Support Ticket | Display error messages for unexpected or unforseen scenarios | 2023-11-03 | 2023-11-03 | 80% | Alan

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | 02. Menu Selection | 2.02 | Add To Cart | Implement core functionality
2 | 02. Menu Selection | 2.02 | Add To Cart | Implement GUI requirments
3 | 02. Menu Selection | 2.02 | Add To Cart | Test if the customized product is added to the cart
4 | 02. Menu Selection | 2.02 | Add To Cart | Test if the price of the cart is updated
5 | 02. Menu Selection | 2.02 | Add To Cart | Stacking the same type of pizza in the cart
6 | 02. Menu Selection | 2.02 | Add To Cart | Ensure the customer can add a maximum of 10 pizzas per order
7 | 02. Menu Selection | 2.02 | Add To Cart | Emptying the cart if the account is inactive for 30mins
8 | 02. Menu Selection | 2.02 | Add To Cart | Notifying the customer after emptying the cart
9 | 02. Menu Selection | 2.03 | View Cart | Implement core functionality
10 | 02. Menu Selection | 2.03 | View Cart | Implement GUI requirments
11 | 02. Menu Selection | 2.03 | View Cart | Test the dedicated View cart page in the user interface
12 | 02. Menu Selection | 2.03 | View Cart | Ensure clear, organized cart view with toppings and customizations
13 | 02. Menu Selection | 2.03 | View Cart | Test If empty cart at checkout, show the message to add items
14 | 02. Menu Selection | 2.03 | View Cart | Display cart cost breakdown: items, taxes, and fees clearly.
15 | 06. Advertising | 6.02 | Modify Ads | Implement core functionality
16 | 06. Advertising | 6.02 | Modify Ads | Implement GUI requirments
17 | 06. Advertising | 6.02 | Modify Ads | Ensure that the authorized user has access to modify the ad
18 | 06. Advertising | 6.02 | Modify Ads | Tracking the modifications for auditing
19 | 06. Advertising | 6.02 | Modify Ads | Display the updated calculated cost to the ad manager
20 | 06. Advertising | 6.02 | Modify Ads | Ensure that predefined format is maintained during modifications
21 | 06. Advertising | 6.03 | Delete Ads | Implement core functionality
22 | 06. Advertising | 6.03 | Delete Ads | Implement GUI requirments
23 | 06. Advertising | 6.03 | Delete Ads | Ensure that only the authorized managers can delete the ad
24 | 06. Advertising | 6.03 | Delete Ads | Display a confirmation prompt while deleting an ad
25 | 06. Advertising | 6.03 | Delete Ads | Display an unauthorized access message to unauthorized users
26 | 06. Advertising | 6.03 | Delete Ads | Test the ad deletion process
27 | 07. Customer Support | 7.02 | Open Support Ticket | Implement basic support ticket creation functionality
28 | 07. Customer Support | 7.02 | Open Support Ticket | Implement email notifications for ticket creations and status updates
29 | 07. Customer Support | 7.02 | Open Support Ticket | Notify the user requesting missing details
30 | 07. Customer Support | 7.02 | Open Support Ticket | Implement ticket escalation timer to notify supervisors
31 | 07. Customer Support | 7.02 | Open Support Ticket | Notify user once the ticket is resolved and request for confirmation
32 | 07. Customer Support | 7.02 | Close Support Ticket | Implement close ticket functionality
33 | 07. Customer Support | 7.02 | Close Support Ticket | Implement comments/notes section after close action is performed.
34 | 07. Customer Support | 7.03 | Close Support Ticket | Implement archive functionality for closed tickets
35 | 07. Customer Support | 7.03 | Close Support Ticket | Display close option only for support agent roles.
36 | 07. Customer Support | 7.03 | Close Support Ticket | Display close option only for resolved tickets.
37 | 07. Customer Support | 7.03 | Close Support Ticket | Verify archived tickets accessability for future reference.
38 | 07. Customer Support | 7.03 | Close Support Ticket | Display error messages for unexpected or unforseen scenarios