## Initial Plan
Color Coding |  |  | Completed |  |  | SPRING 2023 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 15
[5 empty] | Date | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-03-21 | 2023-03-28 | 2023-04-04 | 2023-04-11 | 2023-04-18 | 2023-04-25 | 2023-05-02 | 2023-05-09
HIGH-LEVEL PHASE | ACTIVITY | TASK OWNER | START DATE | END DATE | Progress %
| Project Proposal discussion | Yash Kantharia | 1/20/23 | 1/24/23 | 100%
| Prioritize Project Ideas | Yash Kantharia | 1/25/23 | 1/31/23 | 100%
PROJECT INITIATION | Estimation of cost and schedule | Yash Kantharia/Poonam Adtani/Sarvesh Desai | 1/25/23 | 1/31/23 | 0%
| Development of the business case | Yash Kantharia/Sarvesh Desai | 1/25/23 | 1/31/23 | 100%
| Project environment preparations | Sarvesh Desai/Poonam Adtani | 1/25/23 | 1/31/23 | 0%
MILESTONE 1: INITIAL PROJECT PLAN
| Production of the project schedule | Yash Kantharia | 2023-01-02 | 2023-07-02 | 0%
| Determine project features | Yash Kantharia/Sarvesh Desai/Poonam Adtani | 2023-01-02 | 2023-07-02 | 0%
| Organize project team | Yash Kantharia | 2023-01-02 | 2023-07-02 | 0%
DISCOVERY AND PLANNING | Definition of software Methodology | Poonam Adtani | 2023-01-02 | 2023-07-02 | 0%
| Gathering of business Requirements | Alan Parmar/Sarvesh Desai | 2023-08-02 | 2/14/23 | 0%
| Business Requirements Analysis | Alan Parmar/Sarvesh Desai | 2/14/23 | 2/21/23 | 0%
| System Requirements definition | Poonam Adtani | 2/14/23 | 2/21/23 | 0%
| Requirements prioritization | Poonam Adtani/Yash Kantharia/Sarvesh Desai | 2/21/23 | 2/28/23 | 0%
MILESTONE 1: INITIAL PROJECT PLAN |  |  |  |  | 0%
| Architecture Design | Poonam Adtani/Maneesha Narahari | 2023-01-03 | 2023-08-03 | 0%
| Database Design | Maneesha Narahari | 2023-01-03 | 2023-08-03
DESIGN | System Interface Design | Sarvesh Desai/Poonam Adtani | 2023-08-03 | 3/15/23 | 0%
| User interface design | Sarvesh Desai | 2023-08-03 | 3/14/23 | 0%
MILESTONE 1: INITIAL PROJECT PLAN |  |  |  |  | 0%
| Code Design | Poonam Adtani/Tharun Reddy | 3/21/23 | 3/28/23 | 0%
DEVELOPMENT | Coding | All | 3/21/23 | 2023-04-04
| Unit testing | Saichand Reddy | 3/21/23 | 2023-04-04 | 0%
MILESTONE 1: INITIAL PROJECT PLAN |  |  |  |  | 0%
| Deployment of application testing environment | Poonam Adtani/Saichand Reddy | 2023-04-04 | 2023-04-11 | 0%
| Development of Test Strategy | Saichand Reddy | 2023-04-04 | 2023-04-11
| Test planning | Saichand Reddy | 2023-11-04 | 4/18/23 | 0%
INTEGRATION AND TESTING | Test Cases Design | Saichand Reddy/Poonam Adtani/Sarvesh Desai | 2023-11-04 | 4/18/23 | 0%
| Test Cases Preparation | Saichand Reddy/Poonam Adtani | 2023-11-04 | 4/18/23 | 0%
| Test Cases Execution | Saichand Reddy | 2023-11-04 | 4/18/23 | 0%
| Test Results and Analysis | Poonam Adtani/Saichand Reddy | 2023-11-04 | 4/18/23 | 0%
MILESTONE 1: INITIAL PROJECT PLAN
Implementation | Deployment of Application to production | All | 4/25/23 | 2023-02-05 | 0%