## Initial Plan
Color Coding |  | Completed |  |  |  | SPRING 2023 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | Date | 2023-01-31 | 2023-02-07 | 2023-02-14 | 2023-02-21 | 2023-02-28 | 2023-03-07 | 2023-03-14 | 2023-03-21 | 2023-03-28 | 2023-04-04 | 2023-04-11 | 2023-04-18 | 2023-04-25 | 2023-05-02 | 2023-05-09
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals | Yash Kantharia | 2023-01-20 | 2023-01-24 | 100%
| Confirm Project Team Roles | Yash Kantharia | 2023-01-25 | 2023-01-31 | 100%
| Develop two business cases | Yash Kantharia/Poonam Adtani/Maneesha Narahari | 2023-01-25 | 2023-01-31 | 100%
| Develop Project Initiation Document (PID) | ALL | 2023-01-25 | 2023-01-31 | 100%
| Produce initial Project Plan, RACI | Maneesha / Tharun Reddy | 2023-01-25 | 2023-01-31 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Yash Kantharia | 2023-02-01 | 2023-02-07 | 0%
| Produce Context Diagram, Define System Interfaces | Yash Kantharia/Sarvesh Desai/Poonam Adtani | 2023-02-01 | 2023-02-07 | 0%
| Define Business Requirements | Yash Kantharia | 2023-02-01 | 2023-02-07 | 0%
| Produce Architecture Diagrams | Poonam Adtani/Sarvesh Desai/Maneesha Narahari | 2023-02-01 | 2023-02-07 | 0%
| Define Functional Decomposition | Alan Parmar/Sarvesh Desai | 2023-02-08 | 2023-02-14 | 0%
| Produce RCT document | Alan Parmar/Sarvesh Desai | 2023-02-14 | 2023-02-21 | 0%
| Decide which features to implement this semester | Poonam Adtani | 2023-02-14 | 2023-02-21 | 0%
| Produce analysis diagrams (UML, DFD) | Poonam Adtani/Yash Kantharia/Sarvesh Desai | 2023-02-14 | 2023-02-21 | 0%
| Define functional requirements (User Stories) | Maneesha/ Tharun Reddy | 2023-02-21 | 2023-02-28 | 0%
| Update Project Plan with additional requirements tasks | Maneesha/ Tharun Reddy | 2023-02-21 | 2023-02-28 | 0%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (Class, Sequence Diagrams) | Poonam Adtani/Maneesha Narahari | 2023-03-01 | 2023-03-07 | 0%
| Database Design (ERD, Table spec) | Maneesha Narahari | 2023-03-01 | 2023-03-07 | 0%
| System Interface Design | Sarvesh Desai/Poonam Adtani | 2023-03-08 | 2023-03-21 | 0%
| User interface design | Sarvesh Desai | 2023-03-08 | 2023-03-21 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | GUI & Functionality Detailed Design | Poonam Adtani/ Tharun Reddy | 2023-03-21 | 2023-03-28 | 0%
| Establish code repository in GitHUb | Poonam Adtani/ Tharun Reddy | 2023-03-28 | 2023-04-04 | 0%
| Coding & Implemenation | ALL | 2023-03-28 | 2023-04-04 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | Saichand/ Poonam | 2023-04-04 | 2023-04-11 | 0%
| Evaluate Features to be Tested | Saichand/ Poonam | 2023-04-04 | 2023-04-11 | 0%
| Design Test Cases | Saichand/ Poonam | 2023-04-12 | 2023-04-18 | 0%
| Execute Test Cases | Saichand/ Poonam | 2023-04-12 | 2023-04-18 | 0%
| Anaylze Test Results | ALL | 2023-04-19 | 2023-04-25 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation PowerPoint | ALL | 2023-04-26 | 2023-05-09 | 0%